# Happy Farm Spring Opening

General flow: This is a DOM service. Practice and community are priorities. Work and task accomplishment are secondary to community, safety, play and practice.

Core values: community, safety, practice, happiness, cooperation, teamwork, play

## Farm Task Wish List

- Plant all of our new seedlings: about 700 plants, labeled and organized (sequence: bed prep, drip line replacement, transplant). Do some direct seeding if time permits (beds must be raked and prepped, irrigation systems laid out).

- Mulch entire garden: 3-4” all beds, all tarp covered areas, all pathways and borders, outside edge of farm. Also can do tea, tool and bathroom areas if time allows.

- Prep and clean the sisters garden area (includes removing dead plants, past maturity plants like basil and chard, weeding, relocating mint to near fruit trees, mulching, resetting drip line) / harvest all remaining plants (chard, mint, kale, mustard) to distribute to friends

- Clean the back (west side) of the garden area: put away tools, remove all debris and objects, reconnect/relocate drip lines

- Clean and clear compost area / compost all weeds removed / compost all plates

- Make dripline tensioner weights (gravel in burlap), find 1/2”x30” straight eucalyptus for tensioners (strip and clean)

- Remove logs from main pathways and driveways, clear forest areas of fallen logs, collect firewood and transport. Organize and stack firewood and brush near the south side fence area

- Farm cleanup: Remove all debris and trash from farm areas. clean and mark tools, organize tool areas

- Harvest wheat if ready

- Remove all palm seedlings from garden and surrounding areas / clean and tidy sitting areas

Organize 10 work teams of approximately 10-20+ people each, with one family leader

## General Logistical Support

- Safety support: first aid, emergency response, first aid transport (Aaron)

- Practice support: introductions/invitations, bells, songs, practice guidance, meal guidance, happy working and practice encouragement

- Transportation support: food transport to ‘farm house’, tools, equipment, supplies (vehicle for shuttling procuring tools etc)

- Human support: snacks, water, drinks, shade/shelter/seating, resting spaces, humanure toilets checking (soap, buckets, water, TP, sawdust), parking

- Meal support: food related transport and preparation, extra utensils, wash up bins

Organize 5 teams of 5-10 people for each team. 5 family leaders.

## Long Term Goals

- Build DP community

- Establish community of farm support: people we trust to come regularly on Saturdays

- Establish financial support: regular donations, 1 time donations

## Materials to Transport and Have Available

- Wheelbarrows

- Water

- Ice

- Ice chests

- Buckets (+15 total)

- Shovels

- Bell

- Caution tape

- First aid kit

- Hand towels

- Serving utensils

- Planting layout boards

- Hand washing water system

- Task descriptions

- Tables and wash-up bins, sponges, soap, towels

- Mic and speaker from med hall

- Clip board/signup sheet

- Chainsaws + sharpening tools.

- Long extension cord + power strip, wood burner, etch tool

## Tasks to Complete Before Day Of

- Email friends

- Setup stakes for drip tensioners

- Recover garden hose from sisters

- Collect trees from Sr. Abbess

- Assemble and test Johnny Seeds pinpoint seeder

- Prepare on site parking (front of farm)

- Prepare house

- Contact Angela regarding use of house

- Donation link and display

## Day-of Tasks

- Get ice

## Planting Summary

Row length: 70 ft

### Transplants

| Crop | Variety | Expected lbs/wk | Expected row ft | Rows |
| --- | --- | --- | --- | --- |
| Broccoli | Belstar F1 | 19 | 24 | 0.3 |
| Broccoli | Happy Rich F1 | 10 | 29 | 0.4 |
| Cabbage | Bronco F1 | 58 | 29 | 0.4 |
| Cauliflower | Tessaury F1 | 29 | 43 | 0.6 |
| Chinese Cabbage | Bilko F1 Chinese Cabbage | 43 | 43 | 0.6 |
| Pak Choi | Black Summer F1 | 14 | 32 | 0.5 |
| Lettuce (Single) | Sunland | 40 | 38 | 0.5 |
| Beets | Boldor | 10 | 38 | 0.5 |
| Beets | Boro F1 | 10 | 38 | 0.5 |
| Kale | Black magic | - | 80 | 1 |
| Total |  | 233 | 314 | 5.5 |

### Direct Sow

| Crop | Variety | Expected lbs/wk | Expected row ft | Rows |
| --- | --- | --- | --- | --- |
| Arugula | Wild Arugula | 6 | 64 | 0.9 |
| Chicory | Gourmet Blend | 10 | 63 | 0.9 |
| Greens Mixes | Ovation Greens Mix | 5 | 31 | 0.4 |
| Lettuce (Mixed) | Allstar Gourmet Mix | 10 | 62 | 0.9 |
| Mustard Greens | Wasabina | 5 | 32 | 0.5 |
| Spinach | Corvair | 5 | 4 | 0.1 |
| Carrots | Bengala F1 | 30 | 22 | 0.3 |
| Carrots | Bolero F1 | 30 | 22 | 0.3 |
| Radishes | Sora | 20 | 22 | 0.3 |
| Total |  | 121 | 322 | 4.6 |

## E-mail Update

### General Info

- We expect between 120 and 180 people. Please come in the spirit of working together, flexibility and community building! This is a very special day and will depend on all of us to generate a positive nurturing collective energy.

- With a large group, not all of us will be working the whole time! Be prepared for some lazy time, to enjoy connecting and visiting the farm.

- If you will not be able to attend, please let us know by email as soon as you can, so that we can plan accordingly.

### What to Bring

- Hat, sunscreen, water

- Work gloves, closed-toed sturdy work shoes

- Water will be supplied, but you may prefer having your own bottle

- Utensils for eating: plates, bowls, silverware, cups. We will have a washing up area to wash your items

- Food to share, or if you prefer, your own personal food (especially if you have special dietary restrictions)

- Utensils for serving if you have. Please mark your serving utensils and serving container (name and number)!

- For food that should be kept cool: please bring a cooler with ice if you have. We will have some limited refrigeration space

- Any personal items you will need during the day (especially important: anything for allergies or other medical issues you may have)

### Parking

We have a limited parking area. You will be directed to parking areas. Please carpool if you can! Link here.

### Snacks

We will have times for breaks and visiting. If you would like to bring some simple snacks (fruit, chips, nuts, etc.) to share during the breaks, please send us an email to let us know!

### Support

We could definitely use extra organizing hands! If you would like to help organize and have been to the Happy Farm or the monastery before and can arrive before 8:30am, please fill out this form. Thank you!

### Extra Tools Needed

- Garden weeding tools (weeding knife, scissors, shears)

- Wheelbarrows

## Team Task Breakouts

### Seedling Team (Karmen + Carl)

Team size: ~20 people

This team handles all transplanting and direct seeding. We’ll use the bed-spacing line tool for consistent plant placement.

#### Bed Preparation (Before Planting)

Each bed must be prepared before transplanting or seeding:

- Weed the bed - Remove all weeds, roots and all

- Level and rake - Smooth the soil surface

- Check/replace drip lines - Replace and attach drip lines, make sure functional

- For direct sow beds only:

  - Clear all mulch from bed surface

  - Rake to fine, level tilth

  - Set up sprinkler system (3 rotating sprayers per 80 ft row, covering 2-3 rows)

  - Connect sprinklers to hoses

#### Planting Patterns

We use a 30” × 30” grid (bed width), subdivided into 4×4 squares of 7.5” each. The bed-spacing line marks this grid.

Edge inset rule: All patterns inset plants ~3.75” from bed edges to protect from trampling. This means:

- Pattern 4 (between-grid) is our maximum density - plants are centered in squares, naturally inset

- Patterns 3, 2, and 5-star also inset from edges by ~3.75”

Pattern 4 (7.5" spacing)       Pattern 3 (15" spacing)
16 plants per 30" section      9 plants per 30" section
BETWEEN-GRID (centers)         ON-GRID, inset from edge
~3.75" edge inset              ~3.75" edge inset

   *  *  *  *                     *     *     *
   *  *  *  *                     *     *     *
   *  *  *  *                     *     *     *
   *  *  *  *


Pattern 2 (30" spacing)        5-Star (~15-21" spacing)
4 plants per 30" section       5 plants per 30" section
ON-GRID, inset from edge       ON-GRID, inset from edge
~3.75" edge inset              ~3.75" edge inset

   *        *                     *        *
                                      *
   *        *                     *        *


3x5 Row Pattern (10" between rows, 7.5" in-row)
15 plants per 30" section
FOR CROPS THAT DON'T FIT GRID (beets, etc.)
Outer rows inset ~5" from edge

   *     *     *
   *     *     *
   *     *     *
   *     *     *
   *     *     *

#### Transplant Spacing Guide

Use the bed-spacing line to mark plant positions. Space transplants according to this guide:

| Crop | Variety | Pattern | Spacing | Row Ft | Notes |
| --- | --- | --- | --- | --- | --- |
| Broccoli | Belstar F1 | 2 | 30” | 36 | Large single heads |
| Broccoli | Happy Rich F1 | 3 | 15” | 24 | Sprouting type, multi-harvest |
| Cabbage | Bronco F1 | 2 | 30” | 36 | Heads need space |
| Cauliflower | Tessaury F1 | 2 | 30” | 36 | Large plants |
| Chinese Cabbage | Bilko F1 | 2 | 30” | 36 | Upright, 18-30” recommended |
| Pak Choi | Black Summer F1 | 3 | 15” | 32 | Compact, 12-18” recommended |
| Lettuce (Single) | Sunland | 5-star | ~15” | 39 | 10-12” recommended |
| Beets | Boldor | 3x5 | 10” × 7.5” | 12 | 3 rows, 7.5” in-row |
| Beets | Boro F1 | 3x5 | 10” × 7.5” | 12 | 3 rows, 7.5” in-row |
| Kale | Black Magic | 5-star | ~15” | 85 | 128 plants ordered separately |

Broccoli note: Belstar is a standard heading type (single large head harvest) - needs full 30” spacing. Happy Rich is a sprouting type that produces smaller florets continuously over weeks - can be planted closer at 15” (pattern 3) for higher yield.

Beets note: These are mature transplants (no thinning needed). Use 3x5 row pattern: 3 rows across the bed (10” apart), 7.5” spacing in-row. This gives ~4” clearance for 3”+ diameter beets.

Transplanting tips:

- Dig hole slightly larger than root ball

- Plant at same depth as in cell tray (or slightly deeper for leggy seedlings)

- Firm soil gently around roots

- Water immediately after transplanting

#### Direct Sow Spacing Guide

Seeder row configurations (3 passes across 30” bed):

- 3×4 = 12 rows @ ~2.5” spacing (intensive baby crops)

- 3×2 = 6 rows @ ~5” spacing (carrots, radishes, spinach)

- 3×1 = 3 rows @ ~10” spacing (full-size greens)

| Crop | Variety | Method | Seeder Pattern | Depth | Row Ft | Notes |
| --- | --- | --- | --- | --- | --- | --- |
| Arugula | Wild Arugula | Scatter | - | 1/16” | 64 | Baby leaf, rake in lightly |
| Greens Mix | Ovation | Scatter | - | 1/8” | 31 | Baby leaf, rake in lightly |
| Lettuce (Mixed) | Allstar Gourmet | Scatter | - | 1/8” | 62 | Baby leaf, rake in lightly |
| Mustard Greens | Wasabina | Scatter | - | 1/4” | 32 | Baby leaf, rake in lightly |
| Chicory | Gourmet Blend | Seeder | 3×1 = 3 rows @ 10” | 1/4” | 32 | Thin to 12” |
| Spinach | Corvair | Seeder | 3×2 = 6 rows @ 5” | 1/2” | 3 | Thin to 4-6” |
| Carrots | Bengala F1 | Seeder | 3×2 = 6 rows @ 5” | 1/4” | 11 | Thin to 2” |
| Carrots | Bolero F1 | Seeder | 3×2 = 6 rows @ 5” | 1/4” | 11 | Thin to 2” |
| Radishes | Sora | Seeder | 3×2 = 6 rows @ 5” | 1/4” | 4 | Thin to 2-3” |

#### Scatter Method (Baby Greens)

For arugula, greens mix, and baby lettuce:

- Rake bed to fine, level tilth

- Broadcast seed evenly across bed surface

- Rake lightly to cover seeds (1/16” - 1/8” depth)

- Tamp gently with back of rake or board

- Water with fine mist - keep consistently moist

#### Using the Johnny’s Seeds Pinpoint Seeder

The 4-row pinpoint seeder plants rows at 2¼” apart. For a 30” bed, make 3 passes:

Row configurations:

- Use all 4 hoppers: 3×4 = 12 rows @ ~2.5” (intensive)

- Use 2 hoppers: 3×2 = 6 rows @ ~5” (standard root crops)

- Use 1 hopper: 3×1 = 3 rows @ ~10” (full-size greens)

Operating steps:

- Fill hopper(s) with seeds (one variety at a time)

- Select seed plate - Match hole size to seed:

  - Small holes: Carrots, spinach

  - Medium holes: Radishes, mustard, chicory

- Set furrow depth - Adjust opener to match planting depth

- Make 3 passes - Walk at steady pace, align wheels with previous pass marks

- Cover seeds - Drag chain covers lightly; rake larger seeds if needed

- Mark rows - Use stakes/flags to identify what was planted

Tips:

- Practice on a short section first

- Keep hoppers from running empty (causes gaps)

- Clean between varieties to prevent mixing

- For very small seeds, mix with sand for visibility

#### Irrigation Setup for Direct Sow Beds

- 3 rotating sprayers per 80 ft row

- Sprayers should cover 2-3 adjacent rows

- Connect to main hose line

- Test water pressure and coverage before leaving bed

- Direct sow seeds need consistent moisture for germination - sprinklers should run 2-3x daily for first 2 weeks

### Mulch Team (Dave + AWU Volunteer)

Team size: 15-40 people (depending on turnout)

This team handles all mulching across the farm. Target depth is 4” everywhere (some areas may need more).

#### Mulching Priorities

Work in this order:

- Prep/Organizing - Collect tools, review systems, orient to mulch piles, remove any debris/objects in paths (garden hoses, etc.)

- Garden beds - Start with plastic-covered beds first (see below), then transplant beds

- Aisles - All pathways between beds

- Inner farm borders - Edges inside the main garden area

- Seating areas - Around benches and gathering spots

- Toilet area - Humanure station surroundings

- Outer edges - Starting with west side (cover existing cardboard)

#### Before Mulching

Plastic-covered beds - handle first:

- Remove plastic carefully (avoid tearing)

- Fold neatly

- Store under/near solar panels (shaded area keeps plastic from degrading)

Remove palm seedlings! Palm seedlings must be weeded out before mulching - they’ll push right through mulch if just covered.

- Use a shovel to dig out roots completely

- Get ALL roots - they’ll regrow if left behind

- Compost pulled seedlings

#### Mulching Guidelines

- Target depth: 4” minimum everywhere

- Around plants: Keep mulch 2-3” away from plant stems (prevents rot)

- On cardboard: Apply extra depth (5-6”) to hold cardboard down and speed decomposition

- Aisles: Can go thicker (4-6”) for durability

#### Associated Task: West Side Cleanup

Before mulching the west side border, this area needs clearing:

- Remove all tools - Return to tool area or shed

- Remove palettes - Stack near firewood area or dispose

- Remove debris and trash - Bag trash, compost organic debris

- Relocate drip lines - Move any drip lines back inside garden beds where they belong

#### Workflow

- Start with beds - Split team: some weed palm seedlings ahead, others follow with mulch

- Wheelbarrow brigade - Keep steady flow of mulch from pile to work areas

- Spread and level - Use rakes to spread evenly to 4” depth

- Move outward - After beds, work through aisles → borders → seating → edges

- West side last - Clean up debris first, then mulch over cardboard

#### Follow-on Task: Compost

Once Sisters Garden area has been weeded, add weeds to compost pile. Dave manages the compost - he’ll direct placement and layering.

- All pulled weeds → compost pile

- Organic debris from cleanup → compost pile

- Compostable plates from meal → compost pile (NOT trash)

### Sisters Garden Team (Michael D + Plant-Knowledgeable Volunteer)

Team size: 10-15 people

This team cleans and preps the Sisters Garden area. Critical: Do not remove plants we want to keep!

#### Plants to KEEP

These plants must NOT be removed:

- Garlic - Green shoots, papery bulbs underground

- Edible chrysanthemum - Leafy greens with distinctive smell

- Sweet potato leaves - Heart-shaped leaves on trailing vines

- Bitter melon - Vine with lobed leaves, warty fruit

Rule: If in doubt, leave it! Ask Michael D or the plant-knowledgeable volunteer before removing anything unfamiliar.

#### Tools

- Row flattening boards (for crimping dead crops)

- Hand shears

- Scissors

- Short sickle weeders

- Knives

Safety warning: Sickles and knives are dangerous tools. Use with great care. Keep blades pointed down/away. Be aware of people nearby.

#### Workflow

- Identify keepers first - Walk the area and flag/mark plants to keep

- Remove dead/spent plants - Basil, chard, and other past-maturity crops

- Weed thoroughly - Remove grass, palm seedlings, unwanted plants

- Flatten with boards - Use crimping boards on dead material

- Mulch cleared areas - Once weeded and flattened, apply 4” mulch

- Pull drip lines through - Drip lines can stay in place, just pull up through the mulch

#### Special: Seedy Grasses

For grasses that have gone to seed:

- Cut seed heads FIRST - into a plastic bag

- Seal the bag

- THEN remove the grass stalks

- Dispose of seed heads in trash (NOT compost)

This prevents spreading grass seed throughout the garden.

#### Harvest for Friends

Harvest remaining edible plants to distribute:

- Chard

- Mint (relocate roots to near fruit trees)

- Kale

- Mustard greens

Bag harvested greens and set aside for distribution at the end of the day.

### Drip Line Tensioner Team (AWU Volunteer)

Team size: 5-6 people

This team makes drip line tensioner weights and dowels. Target: supplies for 8 rows.

#### Materials Needed

- Burlap

- Gravel

- Old cotton (optional liners)

- Eucalyptus branches (~1/2” diameter, 30” long, straight)

#### Targets

- 24 weights (3 per row × 8 rows)

- 16 dowels (2 per row × 8 rows)

#### Making Weights

- Cut burlap into ~10” squares

- Optional: line with old cotton

- Fill with 2-3 cups of gravel

- Fold up corners and tie off securely

#### Making Dowels

- Find straight eucalyptus branches (~1/2” diameter)

- Cut to 30” length

- Strip bark and clean

### Wood Movement Team (Ilyas + AWU Volunteer)

Team size: 10-15 people

This team handles log removal and firewood organization. Details from Ilyas.

#### Tasks

- Remove logs from main pathways and driveways

- Clear fallen logs from forest areas

- Collect and transport firewood

- Stack firewood and brush near south side fence area

### Tool Care Team

Team size: 4 people

This team organizes, cleans, and labels tools and equipment across three storage areas.

#### Storage Areas

- Tool/Storage Rack - main hand tools, farm supplies and equipment

- Tool Lock Box - secured items (for our more expensive tools)

- Under Garden Table - overflow and larger equipment

#### Tasks

Organizing:

- Group like tools together (all shovels in one area, all hoes together, etc.)

- Arrange by tool type and size

- Ensure frequently used tools are easily accessible

Cleaning:

- Remove dirt, mud, and debris from all tools

- Wipe down handles

- Clean metal surfaces

Labeling:

- Label tools for identification

- Labeling options available:

  - Sharpie marker (quick labels)

  - Dremel-style etcher (permanent on metal)

  - Wood burner (permanent on wooden handles)

Garden Table Support:

- Install wooden supports under garden table to prevent sinking into ground

- Check table stability after installation